**Subject:** Project: Urban Mobility App – Planning Notes from Kickoff Meeting

Team, here are the planning notes from today’s session. Please consolidate and move things to the tracker.

* Kickoff confirmed for **July 1, 2025**.
* Set up dev environment. [Frank] will lead.
* Wireframes (UI/UX) to be drafted by [Aditi] between July 2–3.
* API gateway setup by [Neel] from July 4–6.
* Core backend logic design — [Meena], July 5 to July 8.
* Frontend React integration — [Tom], July 9–12.
* Authentication module (OAuth2) — [Zara], July 10–11.
* Database schema finalization — [Kishore], July 6–7.
* CI/CD pipeline — [Jai], planned for July 13–14.
* Internal security audit to be done by [Lena] on July 15.
* Admin dashboard prototype — [Aditi], July 16–18.
* Load testing (basic) — [Meena], July 19–20.
* Final UAT — [Lena], between July 21 and July 22.
* Marketing collateral draft — [Shreya], July 23–24.
* Stakeholder demo and sign-off — [Tom], July 25.